## Status Report
Status Report for Team 5
Project |  | Status: (Red/Yellow/Green)
Date: | 2024-05-20 | Overall Status: | Green
Contact: | Alex Smith | Explanation: | Development going smoothly so far.
Prepared By: | Alex Smith
Key Accomplishments
List key tasks and milestones achieved in this period, along with any key changes
Person Name | Task
Tobi | Third party API calls working on front end, search functionality working
Alex | Flowchart and backend structure made
Dahir | ERD designed
Hassan | Class diagram made and Database implemented
ID # | Key Issues | Action Plan |  |  | Status
None
1 | Secure logins/sessions | Research, then try to implement |  |  | Found a way to do security with spring boot, need to figure out how to do secure API calls
Critical Milestones |  | Health | Due Date | Comment/Status %
| Get app requirements | Green | 20/05 | Finished
| Create diagrams | Green | 20/05 | Finished
| Program interfaces | Green | 20/05 | Finished (for now)
| Database sql doc made | Green | 20/05 | Finished (for now)
| Front end | Green | 22/05 | In progress
| DAOs implemented | Green | 21/05 | In progress
| Service layers implemented | Green | 21/05 | Started
| Controllers implemented | Green | 21/05 | Not started
| Unit tests | Green | 21/05 | Not started
| Finish critical user stories | Green | 22/05 | Not started
| (stretch) Shopping list user story | Green | 23/05 | Not started
| Presentation complete | Green | 23/05 | Not started