## Status Report
Status Report for Team 5
Project |  | Status: (Red/Yellow/Green)
Date: | 2024-05-20 | Overall Status: | Green
Contact: | Hassan Yusuf | Explanation: | On track with development, no roadblocks
Prepared By: | Hassan Yusuf
Key Accomplishments
List key tasks and milestones achieved in this period, along with any key changes
Person Name | Task
Tobi | Working mostly with the register and login functions on the frontend
Alex | Working on backend functionality and making sure features work as expected/debugging
Dahir | Working on the service layer unit tests
Hassan | Working on getting the password encryption working correctly
ID # | Key Issues | Action Plan |  |  | Status
None
1 | Secure logins/sessions | Research, then try to implement |  |  | Resolved
Critical Milestones |  | Health | Due Date | Comment/Status %
| Get app requirements | Green | 20/05 | Finished
| Create diagrams | Green | 20/05 | Finished
| Program interfaces | Green | 20/05 | Finished
| Database sql doc made | Green | 20/05 | Finished
| Front end | Green | 22/05 | In progress
| DAOs implemented | Green | 21/05 | Finished
| Service layers implemented | Green | 21/05 | Finished
| Controllers implemented | Green | 21/05 | Finished
| Unit tests | Yellow | 21/05 | In progress
| Finish critical user stories | Green | 22/05 | Not started
| (stretch) Shopping list user story | Green | 23/05 | Not started
| Presentation complete | Green | 23/05 | Not started