## Status Report
Status Report for Team 5
Project |  | Status: (Red/Yellow/Green)
Date: | 2024-05-20 | Overall Status: | Green
Contact: | Dahir Noor | Explanation: | On track with development, some frontend to implement
Prepared By: | Dahir Noor
Key Accomplishments
List key tasks and milestones achieved in this period, along with any key changes
Person Name | Task
Tobi | Saving the userId and passing the id with recipe id
Alex | Finishing Testing
Dahir | Finishing Testing
Hassan | Finishing Testing
ID # | Key Issues | Action Plan |  |  | Status
None
1 | Secure logins/sessions | Research, then try to implement |  |  | Resolved
2 | Frontend | Research, then try to implement |  |  | Ongoing
Critical Milestones |  | Health | Due Date | Comment/Status %
| Get app requirements | Green | 20/05 | Finished
| Create diagrams | Green | 20/05 | Finished
| Program interfaces | Green | 20/05 | Finished
| Database sql doc made | Green | 20/05 | Finished
| Front end | Green | 22/05 | In progress
| DAOs implemented | yellow | 21/05 | Finished
| Service layers implemented | Green | 21/05 | Finished
| Controllers implemented | Green | 21/05 | Finished
| Unit tests | Green | 2024-05-22 | Finished
| Integration Testing | Yellow | 2024-05-23 | In progress
| (stretch) Shopping list user story | Yellow | 23/05 | Not started
| Presentation complete | Yellow | 23/05 | In progress