## Status Report
Status Report for Team 5
Project |  | Status: (Red/Yellow/Green)
Date: | 2024-05-23 | Overall Status: | Green
Contact: | Oluwatobi Sobola | Explanation: | Practicing presentation and finishing programming full stack applications.
Prepared By: | Oluwatobi Sobola
Key Accomplishments
List key tasks and milestones achieved in this period, along with any key changes
Person Name | Task
Tobi | Practicing Presentation
Alex | Practicing Presentation
Dahir | Practicing Presentation
Hassan | Practicing Presentation
ID # | Key Issues | Action Plan |  |  | Status
None
1 | Secure logins/sessions | Research, then try to implement |  |  | Resolved
2 | Frontend | Research, then try to implement |  |  | Resolved
Critical Milestones |  | Health | Due Date | Comment/Status %
| Get app requirements | Green | 20/05 | Finished
| Create diagrams | Green | 20/05 | Finished
| Program interfaces | Green | 20/05 | Finished
| Database sql doc made | Green | 20/05 | Finished
| Front end | Green | 23/05 | Finsihed
| DAOs implemented | yellow | 21/05 | Finished
| Service layers implemented | Green | 21/05 | Finished
| Controllers implemented | Green | 21/05 | Finished
| Unit tests | Green | 22/05 | Finished
| Integration Testing | Green | 23/05 | Finished
| (version 2.0) Shopping list user story | Red | 23/05 | Not going to implement
| Presentation complete | Green | 23/05 | Finished